## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Setting up URP Project, algorithm research and small Cell script made | 1 | 2024-05-15 | In this hour I set up the project on Git, resolved an old Sourcetree bug and looked into the different algorithms on the wikipedia page that was mentioned in the assessment PDF. After which I used my findings on the randomized depth-first algorithm to make a small Cell script.
Started grid generation and testing the size of the maze while completely staying in the view of the camera. Found that performance is giant issue. | 2 | 2024-05-16 | Spent 2 hours setting up everything for the maze to generate through a collection of cells and a grid for recursively filling the maze in. Only to reach the part where I setup the camera and stop dead in my tracks due to abysmal performance.
Full performance check to see if my maze idea is even possible due to having to render the whole maze at any size. | 2 | 2024-05-16 | Any maze larger than 100x100 lags out whatever I throw at it, tried using sprite renderers instead of 3d objects to lower the vertice count and by manually batching everything after the built in static batching happens. But it seems I have to start over and this time start with compute shaders, as a maze of 250x250 cells will otherwise just not render. This was made sure by using the profiler which showed me that I had about 300ms cpu waiting time due to rendering alone.
Instead of cell first generation I am now trying wall first generation. | 2 | 2024-05-17 | Instead of having cells with walls, I decided a different approach. Now the walls are generated seperately and this way there's also no more overlapping walls making the amount of triangles lower. These walls are currently generated but I still have to find a way to identify the empty space between the walls as a cell to make the algorithm work.
Finding all cells from knowing where the walls are. | 2 | 2024-05-17 | The walls are generated and the cells are succesfully all found through a seperate class with a function that attempts to find all the cells by going through them in the same order they are generated.
Bugfix for cell array | 1 | 2024-05-17 | The cells were counted but not properly implemented with their actual walls. This is now fixed.
Creating a cell grid from collection of cells. | 3 | 2024-05-22 | Realized that with the current cell collection checking where neighbours is really annoying. So I started work on a cell grid that is made from the collection of cells. This grid will be used to check possible empty neighbours, making the system ready for pretty much every algorithm.
Fixing cell finding and grid construction | 2 | 2024-05-22 | Found many wrong integer casts, and poor calculations in my handling of finding all the cells and placing them into a grid for ease of access. Spent a good two hours fixing all of these and now the randomized depth-first search algorithm is working smoothly.
Implemented algorithm and added comments | 3 | 2024-05-23 | Finalized all grid and cell collection and also finalized the randomized depth-first search with a stack implementation instead of recursive. Had issues with properly assigning the southern wall as my original was very poorly done. Added a lot of comments across the project. Last step is a simple GUI to set the maze parameters and remake mazes.
Total amount of hours | 18